## Summary
GIGW + DBIM Compliance Task Summary
Project | Haryana State Digital Knowledge System (hlks-demo)
Generated | 2026-07-08
By Priority | Count
Medium | 20
Low | 14
High | 8
- | 2
Done | 1
N/A | 1
By Category | Count
Accessibility | 7
Footer | 6
Typography | 5
Content | 5
Logo & Header | 4
Colours | 3
Imagery | 3
Performance | 3
Security | 3
Governance / Process | 3
Search | 2
Forms | 2
Total Items | 46

## Tasks
S.No | Category | Requirement | Guideline Ref (GIGW / DBIM) | Current Status | Gap / Required Action | Priority | Effort | File(s) / Area to Touch | Status
1 | Colours | Adopt one official DBIM primary colour group (currently uses a custom blue #1a56db not present in any DBIM palette) | DBIM 2.1 | Non-compliant | Replace --primary and its shades in index.css with one full DBIM colour group (recommended: 'Blue' group #162F6A / #214AAB / #5279D7 / #A3BBF3 / #D2DFFF) | Medium | S | src/index.css
2 | Colours | Align functional colours (bg/text/status) to DBIM functional palette hex values (Linen #EBEAEA, Inclusive #FFFFFF, Deep Earthy Brown #150202 text, Liberty Green #198754 success, Mustard Yellow #FFC107 warning, Coral Red #DC3545 error, Blue #0D6EFD info/link) | DBIM 2.2 / Table 1 | Partial | Current status colours (#22c55e/#ef4444/#f59e0b/#3b82f6) are close but not the exact mandated hex values; update CSS custom properties | Low | S | src/index.css
3 | Colours | Text/background colour combinations must pass the Do/Dont contrast pairs shown in DBIM | DBIM 4.4, Fig 16-17 | Not verified | Audit and fix low-contrast pairs once the palette (item 1) is finalized (footer secondary text at 40-55% opacity flagged as borderline) | Medium | S | src/components/layout/Footer.jsx, index.css
4 | Typography | Noto Sans as the main typeface, self-hosted (no external CDN dependency) | DBIM 4.1 | Done | Already self-hosted this session (public/fonts + index.css @font-face). No action needed. | Done | - | index.html, src/index.css | Done
5 | Typography | Noto Sans Devanagari support for Hindi content | DBIM 4.2 | Partial | Font is ready but [lang='hi'] CSS rule and skip-nav/contrast block are still inside a disabled comment; no active Hindi content path exists | Medium | S | src/index.css:141-180
6 | Typography | Standardize type scale to DBIM desktop/mobile scale (H1 36/24px, H2 24/20px, H3 20/16px, Para1 16/14px, Para2 14/12px, Small 12/10px) | DBIM 4.3, Table 3-4 | Not verified | Font sizes are currently ad hoc inline values across components; introduce shared type-scale tokens/classes and refactor | Low | L | src/index.css, all page/components
7 | Typography | Body text left-aligned; tables left-align text, right-align numbers, center-align column headers | DBIM 4.1.1 | Partial | Numeric column right-alignment not consistently applied in data tables (e.g. Admin/Nodal dashboards) | Low | M | Dashboard table components
8 | Typography | CTA buttons: max 3 words, consistent padding, distinct enabled/hover/focus/disabled states | DBIM 4.5 | Partial | Some buttons lack a visible focus state; no global focus-visible strategy exists | Medium | M | src/index.css, buttons app-wide
9 | Logo & Header | Use the (State) Emblem in the header per DBIM logo-lockup rules (Lockup 2 for Dept, 3A/3B for orgs) | DBIM 5.1-5.4 | Missing | haryana-logo.png exists as a department logo, but the mandated Emblem + bilingual 'Government of Haryana' text lockup pattern is not implemented; footer still uses an emoji as an 'Ashoka chakra placeholder' | High | M | src/assets, src/components/layout/Sidebar.jsx, Topbar.jsx, Footer.jsx
10 | Logo & Header | Digital India logo/link in header or footer co-branding section (max 2 co-brand logos) | DBIM 5.4 | Missing | No Digital India logo/link anywhere in the codebase | Medium | S | Footer.jsx or Topbar.jsx
11 | Logo & Header | Header must contain: search bar, skip-to-content, language selector, accessibility controls, sticky global nav | DBIM 5.4.1, Fig 42-44 | Partial | Nav + search exist; no visible language-selector or accessibility-controls icon in the header; skip-link CSS exists but is not rendered anywhere | High | M | src/components/layout/Topbar.jsx / Sidebar.jsx
12 | Logo & Header | Correct emblem colour variant: black on white background, white on dark background | DBIM 5.3 | N/A (blocked by #9) | Apply once the emblem asset from item 9 is added | Medium | S | Same as item 9
13 | Footer | Footer must use the key (darkest) colour of the selected DBIM palette | DBIM 5.6 | Needs re-check | Re-verify footer background once the palette (item 1) is finalized | Low | S | src/components/layout/Footer.jsx
14 | Footer | Footer link items (Privacy Policy, Terms of Use, Hyperlink Policy, Copyright Policy, Sitemap, Help/FAQ, Screen Reader Access, Feedback, Contact Us, Accessibility, Disclaimer) must point to real pages | DBIM 5.6 / GIGW | Missing | All footer links are href='#' stubs with no real target page/content | High | L | src/pages/(new pages) + Footer.jsx
15 | Footer | Footer must state lineage using the mandated phrasing per org type (e.g. 'This website belongs to [Department], Government of Haryana') | DBIM 5.6 | Partial | Generic 'Government of Haryana' phrase used instead of the mandated pattern | Low | S | src/components/layout/Footer.jsx
16 | Footer | RTI (Right to Information) link in footer/Connect section | GIGW mandatory | Missing | No RTI link/page exists (RTI only appears as legal-document content in mock data) | High | S | Footer.jsx + new RTI page
17 | Footer | Visitor counter | GIGW common practice | Missing | No visitor counter widget present | Low | M | Footer.jsx + backend endpoint
18 | Footer | 'Last Updated On' date reflecting latest content update | DBIM 5.6 | Partial | A single static date is hardcoded site-wide instead of being per-page/dynamic | Low | M | Footer.jsx
19 | Imagery | Enforce image size limits (background/banner <=500KB, thumbnail <=100KB, high-res <=5MB) | DBIM 6.1.1, Table 6 | Not enforced | No client or server-side validation/compression exists on upload | Medium | M | src/services/pdf.js, upload forms
20 | Imagery | Alt text must be meaningful, <=140 characters, and avoid generic terms like 'image of' | DBIM 6.1.2 | Partial | Several non-decorative logo instances use empty alt='' (AdminOtpLogin.jsx:106, AdminOtpLoginScreen.jsx:103, ChangePasswordScreen.jsx:90, ForgotPasswordScreen.jsx:130) | Medium | S | Listed files above
21 | Imagery | Headshots (if used): white background, 1:1 ratio, face covering 50% of frame | DBIM 6.1.4 | N/A today | Apply if/when an officer directory or profile-photo feature is added | Low | - | -
22 | Content | Functional bilingual (EN/HI) toggle with proper lang and hreflang attributes | DBIM 4.2, 7.5 | Missing | The existing 'Hindi' option in UploaderDashboard is a document-metadata field only, not a site-wide language switcher; [lang='hi'] CSS is unused | High | L | App-wide i18n implementation
23 | Content | Cookie consent banner (accept/reject/customize) per DPDP Act 2023 | DBIM 7.6.1, Fig 40-41 | Missing | No cookie banner or preferences page exists anywhere in the app | High | M | src/App.jsx + new CookieConsent component
24 | Content | Uploaded documents must be accessible PDFs only, no editable formats | DBIM 7.1.3.3 | Not verified | Legal documents appear to be uploaded as-is with no accessibility tagging step | Medium | M | src/pages/UploaderDashboard.jsx, backend
25 | Content | Tone of voice: concise, plain language, no Hinglish, uniform British English | DBIM 7.1.3 | Not audited | Needs a dedicated content/copy review pass | Low | M | App-wide UI copy
26 | Content | Central Content Publishing System (CCPS) integration for whole-of-government banners/posts | DBIM 7.4 | N/A | CCPS is a Central Ministry/MeitY system; not applicable to a State department portal | N/A | - | -
27 | Accessibility | Activate skip-to-main-content link | GIGW / DBIM 8.2 | Partial | CSS for .skip-nav exists but sits inside a disabled comment block labelled 'DBIM / GIGW compliance - enable in production'; no <a> element renders it | High | S | src/index.css:141-180, src/components/layout/Layout.jsx | Done
28 | Accessibility | Text-size adjuster (A+ / A-) | GIGW / DBIM Fig 44 | Partial | CSS (html[data-font-size]) exists but no UI control is wired to it | Medium | M | Topbar.jsx + index.css | Done
29 | Accessibility | High-contrast mode toggle | GIGW / DBIM Fig 44 | Partial | CSS (html[data-contrast="high"]) exists but no UI control is wired to it | Medium | M | Topbar.jsx + index.css | Done
30 | Accessibility | Real Screen Reader Access / Accessibility Statement page | GIGW | Missing | Footer.jsx:15 links to an anchor stub (href='#screen-reader'), not a real page | Medium | S | New page + Footer.jsx | Done
31 | Accessibility | Consistent <label htmlFor> bindings on all form inputs | GIGW / DBIM Annexure B | Partial | Login.jsx uses proper labels; Uploader/Admin forms rely on placeholder text only - zero htmlFor usage found app-wide | Medium | M | All form components
32 | Accessibility | Keyboard navigability with a visible focus-visible state | GIGW / DBIM 8.2 | Partial | Some :focus styles exist but there is no global focus-visible strategy; zero tabIndex usage found | Medium | S | src/index.css
33 | Accessibility | Colour contrast for text over the selected palette | GIGW / DBIM 4.4 | Not verified | Re-run contrast checks once palette (item 1/3) is finalized | Medium | S | -
34 | Search | Enhanced search: multi-language, filtered/categorized results, autocomplete, spell correction, covers PDFs/HTML/metadata | DBIM 9 | Partial | Existing search covers basic keyword matching only; no autocomplete, spell-correction or persona/category filters | Medium | L | Search feature + backend
35 | Search | Consistent search box placement in the header across all pages | DBIM 9(v) | Needs verification | Confirm placement/behaviour is identical on every page/role dashboard | Low | S | Topbar.jsx
36 | Performance | Lazy-load images and media | DBIM 10.1.2 | Not verified | Add loading='lazy' to <img> tags where appropriate | Low | S | App-wide
37 | Performance | Image compression/optimization pipeline before publishing | DBIM 10.3.2 | Not enforced | No compression step exists in the upload flow | Medium | M | Upload backend
38 | Performance | Analytics integration (visitor tracking, KPIs, traffic dashboard) | DBIM 10.5-10.6 | Missing | No analytics/visitor tracking found anywhere in the app | Low | M | index.html / src/main.jsx
39 | Forms | Mandatory fields marked with * or "Required"; single-column vertical layout; clickable labels; keyboard-friendly | DBIM Annexure B | Partial | Login.jsx is mostly compliant; Add Department / User forms are inconsistent (placeholders instead of labels) | Medium | M | Form components across Admin/Uploader/Nodal dashboards
40 | Forms | Primary action buttons disabled until required fields are valid, with submit-progress feedback | DBIM Annexure B(xiv) | Partial | Some forms already do this (e.g. Add Department drawer disables while creating) - extend the pattern to all forms | Low | M | Form components app-wide
41 | Security | CAPTCHA on login/OTP/forgot-password forms | GIGW security baseline | Missing | No CAPTCHA found on any authentication form | High | M | src/pages/Login.jsx, AdminOtpLogin*, ForgotPasswordScreen.jsx | Done
42 | Security | Idle/inactivity session timeout (not just reactive 401 logout) | GIGW | Partial | Only a reactive 401-triggered logout exists (services/api.js:17, hooks/useAuth.js:54-55); no idle timer | Medium | M | src/hooks/useAuth.js
43 | Security | HTTPS enforcement | GIGW | Deployment-level | Not an app-code concern; ensure the hosting/reverse-proxy layer enforces HTTPS | Medium | Process | -
44 | Governance / Process | Nominate a CIO / Web Information Manager for the portal | DBIM Annexure E | Process | Organizational decision, not a code task | - | Process | -
45 | Governance / Process | Submit the site for STQC GIGW 3.0 certification | DBIM / GIGW | Process | Should follow once the High/Medium items above are closed | - | Process | -
46 | Governance / Process | Reference DBIM's 5-section Ministry IA (About Us/Offerings/Documents/Media/Connect) as inspiration only | DBIM Annexure A.1 | Reference only | HLKS is a specialised legal-document repository, not a general Ministry site - literal 5-section nav is not mandatory, but Acts/Rules/Notifications/Circulars structuring can borrow from it | Low | Reference | -